Enterprise Conversational AI Platform
Workstreams and Staffing Model

Operating model for platform delivery, capability scaling, AI quality, and AI COE enablement

# 1. Executive Summary

The enterprise conversational AI platform should be delivered through coordinated workstreams rather than a single monolithic chatbot team. The recommended model separates reusable platform engineering from business capability delivery, AI-assisted development workflow, AI quality and evaluation, operations, cloud/security, and AI COE enablement.

The operating model is designed around one principle: Build the platform once. Build capabilities many times.

# 2. Operating Principles

Business owns the what: outcomes, policy constraints, disclosures, success measures, and acceptance criteria.

Platform owns the runtime: orchestration, state, provider abstractions, capability runtime, response composition, guardrail integration, channel adapters, and reliability.

Capabilities are built from specs: standardized capability specifications, conversation contracts, execution contracts, response contracts, and tests.

AI accelerates delivery but does not remove engineering discipline.

AI Quality starts on day one with behavior-based evaluation, not only late-stage QA.

AI COE enables scale through standards, patterns, guidance, reusable assets, and coaching.

# 3. Recommended Workstreams

| Workstream | Mission | Team size | Core deliverables | Parallelization |
| --- | --- | --- | --- | --- |
| Platform Runtime | Build the reusable conversational runtime and orchestration engine | 5–7 | Session manager, goal manager, LangGraph graph, provider abstraction, capability runtime, tool execution, response composer | Starts day 1 |
| Developer Platform | Build spec-driven workflow and AI-assisted engineering tools | 3–4 | Capability spec templates, Codex/Copilot instructions, scaffolding, CI checks, validation commands | Starts day 1 |
| Capability Pods | Build business capabilities from specs | 3–5 per pod | Capability specs, prompts/contracts, adapters, tests, golden conversations, business signoff | Starts after baseline |
| AI Quality & Evaluation | Create behavior-based testing and evaluation model | 4–6 | Golden conversations, synthetic scenarios, eval gates, regression dashboards, response compliance checks | Starts day 1 |
| Observability / Ops / FinOps | Operate with traceability, cost visibility, and release health | 2–4 | Tracing, dashboards, cost per objective, incident playbooks, release monitoring | Starts day 1 |
| Cloud / Security / Infra | Prepare secure AWS deployment foundation | 4–6 | IAM, secrets, networking, logging, CI/CD environments, security reviews | Starts day 1 |
| AI COE Enablement | Enable teams through standards and coaching | 2–4 matrixed | Reference architecture, prompt/eval standards, guardrail patterns, model guidance, reusable assets | Advisory / ongoing |
| Business Capability Ownership | Define outcomes, policies, and acceptance criteria | 2–3 per domain | Capability backlog, acceptance criteria, disclosure requirements, success metrics, prioritization | Embedded in pods |

# 4. Parallel Delivery Model

## Wave 0 — Alignment and Mobilization: approximately 2 weeks

Confirm executive sponsor and funding model.

Select initial business domain and pilot capabilities.

Confirm common vocabulary and architecture principles.

Assign platform, AI Quality, AI COE, business, and cloud/security leads.

Agree on success metrics and release governance.

## Wave 1 — Platform Foundation and Pilot Capabilities: approximately 6–8 weeks

Build reusable runtime skeleton.

Build spec-driven development workflow.

Implement one or two pilot capabilities.

Establish evaluation and observability baseline.

Prove end-to-end flow from capability spec to runtime execution.

## Wave 2 — First Production Release: approximately 6–8 weeks

Harden platform for production.

Expand to three to five priority capabilities.

Add stronger release gates and monitoring.

Validate business participation and AI Quality process.

## Wave 3 — Scale-Out Capability Factory: approximately 8–12 weeks

Run multiple capability pods in parallel.

Mature AI-assisted development workflow.

Expand evaluation automation and feedback loops.

Establish repeatable governance and release process.

# 5. Staffing Scenarios for Funding Discussion

| Scenario | Approx. staffing | Capability throughput | Best fit |
| --- | --- | --- | --- |
| Lean MVP | 8–12 core contributors | 1 capability pod; 1–2 pilot capabilities | Proof, executive demo, controlled rollout |
| Enterprise Launch | 15–22 contributors | 2 capability pods; 3–5 capabilities | First production business release |
| Scale-Out Factory | 25–40+ contributors across streams | 3+ capability pods; continuous capability onboarding | Enterprise adoption and multi-domain expansion |

Recommended initial ask: Enterprise Launch if the organization expects production readiness rather than a limited proof of concept. A Lean MVP can prove feasibility, but it may underfund quality, observability, cloud/security, and business enablement.

# 6. AI Quality & Evaluation Engineering

Traditional QA is necessary but not sufficient for agentic conversational platforms. The evaluation team should evolve from scripted test execution to behavior-based AI quality engineering.

Define golden conversation scenarios for each capability.

Generate synthetic conversation variations to test robustness.

Validate objective understanding and capability selection.

Validate interruption, pause, resume, and fallback behavior.

Validate response contracts, tone, disclosures, and compliance requirements.

Run safety and hallucination checks.

Maintain regression suites in CI/CD.

Measure production outcomes and feed defects back into specs and tests.

| Metric | Why it matters |
| --- | --- |
| Objective completion rate | Measures whether members accomplish what they came to do |
| Capability selection accuracy | Measures whether the platform selects the right capability |
| Clarification efficiency | Measures whether the agent asks useful questions without unnecessary friction |
| Interruption recovery rate | Measures whether paused goals resume correctly |
| Response compliance rate | Measures whether responses follow templates, disclosures, and policies |
| Fallback/escalation rate | Measures confidence and failure recovery |
| Cost per completed objective | Connects model cost to business value |
| Latency per turn | Measures customer experience and runtime efficiency |
| Tool failure rate | Measures reliability of backend integrations |

# 7. AI COE Enablement Role

The AI COE should be positioned as an enterprise enablement function, not as the team that must deliver every agentic use case.

## AI COE should provide

Reference architectures.

Prompt and specification standards.

Evaluation templates and best practices.

Guardrail and governance patterns.

Model/provider selection guidance.

Reusable assets and training material.

Coaching for capability teams.

Architecture review support for high-risk capabilities.

## AI COE should not become

The only team allowed to build AI capabilities.

The production owner for every capability.

The team that manually reviews every prompt or response.

A delivery bottleneck between business teams and platform adoption.

# 8. Business Participation Model

Capability definition: what member objective should this capability satisfy, and what policies, constraints, disclosures, and success measures apply?

Spec and scenario review: do the capability spec and golden conversations represent real member behavior?

Acceptance and release readiness: does the capability meet business acceptance criteria, response expectations, and operational readiness?

# 9. Key Decision Points for Leadership

Executive sponsor and decision forum.

Initial business domain and first pilot capabilities.

Initial staffing scenario: Lean MVP, Enterprise Launch, or Scale-Out Factory.

AI COE enablement commitment.

AI Quality and Evaluation workstream ownership.

Cloud/security engagement model.

Target release wave and production readiness bar.

Metrics that define success.

# 10. Recommended Next Step

Approve Wave 0 and Wave 1 funding for an Enterprise Launch path: stand up the platform runtime team, stand up the developer platform workflow, assign one or two capability pods, create AI Quality and Evaluation from day one, and include observability, cloud/security, and AI COE partners from the beginning.

This avoids the common failure mode where the prototype works but the organization cannot scale it into a governed production platform.